Channel Go-Live Provisioning Checklist

MobiCova Health — WhatsApp · USSD · SMS Prepared by: MobiCova Health · Date: 19 June 2026 Purpose: Start the long-lead, third-party approvals now — they gate a real public launch and are independent of the language work.

## Why now

The Health Buddy and enrolment flows reach basic phones through WhatsApp, USSD and SMS. Each needs external approvals that take weeks and are not something we can rush at the end. Starting them in parallel with the translation reviews means nothing blocks launch later.

## 1. WhatsApp Business Platform (Meta Cloud API)

| Step | Detail | Owner | Status |
| --- | --- | --- | --- |
| Meta Business verification | Verify the MobiCova business in Meta Business Manager (CAC docs, business details) |  | ☐ |
| WhatsApp Business Account (WABA) | Create WABA; choose/port the sending phone number |  | ☐ |
| Display name approval | Submit the business display name for review |  | ☐ |
| Message templates | Draft + submit templates (enrolment confirmation, OTP, Buddy intro). Utility/auth categories. Each needs approval |  | ☐ |
| Phone number quality / tier | Start on low tier; messaging quality raises limits over time |  | ☐ |
| Webhook + token | Set WHATSAPP_TOKEN, WHATSAPP_PHONE_ID, WHATSAPP_VERIFY_TOKEN in the API service |  | ☐ |
| Opt-in compliance | Confirm users opt in before messaging (WhatsApp policy) |  | ☐ |

Lead time: typically 1–3 weeks (business verification + template approvals are the slow parts). Note: template content should be finalised per language too, but English can launch first.

## 2. USSD short code

| Step | Detail | Owner | Status |
| --- | --- | --- | --- |
| Choose aggregator / telco | Select a USSD aggregator covering MTN, Airtel, Glo, 9mobile |  | ☐ |
| Short code application | Apply for a shared or dedicated short code (e.g. *XYZ#) |  | ☐ |
| Billing model | Confirm session billing (who pays — user/airtime vs sponsored) and per-session cost |  | ☐ |
| Session/character limits | Confirm the 182-char screen limit and session timeout with the aggregator |  | ☐ |
| Endpoint integration | Point the short code to the MobiCova USSD webhook; test on each network |  | ☐ |
| Go-live testing | Live dial test on all four networks |  | ☐ |

Lead time: typically 3–6 weeks (short-code allocation + per-network provisioning). Cost flag: the session billing model is the biggest swing in the comms cost model — confirm early.

## 3. SMS sender ID (NCC)

| Step | Detail | Owner | Status |
| --- | --- | --- | --- |
| Choose SMS provider | Select an SMS gateway/aggregator with Nigerian routes |  | ☐ |
| Register sender ID | Register the alphanumeric sender ID (e.g. “MobiCova”) — unregistered IDs are blocked/filtered in Nigeria |  | ☐ |
| DND / opt-in handling | Confirm handling of Do-Not-Disturb (DND) lists and opt-in for non-transactional messages |  | ☐ |
| Encoding check | Decide GSM-7 vs Unicode (UCS-2). Indigenous-language diacritics force UCS-2 (70 chars/segment) — strip them on SMS to control cost |  | ☐ |
| Delivery reporting | Enable delivery receipts for monitoring |  | ☐ |

Lead time: typically 1–2 weeks (sender-ID registration). Cost flag: keep SMS in plain GSM-7 where possible; Yoruba/Igbo tone marks roughly double-to-triple per-message cost.

## 4. Cross-cutting

- Data & consent: confirm opt-in and privacy wording per channel (ties into the NDPR privacy notice).

- Sandbox vs production: simulators already exist in-app for testing flows without live channels — use them to finalise copy while approvals are pending.

- Monitoring: plan delivery/again-failure alerting once live.

## Suggested order

- Start WhatsApp business verification + USSD short-code application this week (longest poles).

- SMS sender-ID registration (quick) in parallel.

- Finalise template/flow copy using the in-app simulators while approvals process.

- Live-test each channel per network as approvals land.

MobiCova Health — reaching every Nigerian, on the phone they already have.