## Slide 1
Nigerian-Language Support — Investment Summary
Prepared for AXA Mansard
Cost area | Indicative (all 4 languages)
Translation - general (UI + USSD/WhatsApp + email/SMS) | ₦0.8M - 1.4M
Translation - specialist (safety / legal / consent) | ₦0.5M - 0.9M
Native-speaker clinician review & sign-off | ₦2.0M - 3.0M
In-language safety vocabularies | ₦0.3M - 0.5M
Legal review of consent / disclaimers | ₦0.6M - 1.2M
Linguistic QA & testing | ₦0.2M - 0.4M
ONE-OFF TOTAL (external, ~$2.8k - 4.6k) | ₦4.4M - 7.4M
Recurring (ongoing) | ₦0.6M - 1.4M / year
Indicative planning ranges, not a quote. Cost is driven by clinical & legal review, not software. Rollout: Pidgin -> Hausa -> Yoruba -> Igbo; first language live ~6-8 weeks from go-ahead, all four ~4-5 months.

## Slide 2
Indicative Delivery Timeline
Prepared for AXA Mansard
Pidgin live ~wk 8
All four ~wk 20
Phase 0 — Foundation
Wk 1–3
Phase 1 — Nigerian Pidgin
Wk 3–8
Phase 2 — Hausa
Wk 8–12
Phase 3 — Yoruba
Wk 12–16
Phase 4 — Igbo
Wk 16–20
Wk 0
Wk 4
Wk 8
Wk 12
Wk 16
Wk 20
Indicative only; weeks are elapsed time from go-ahead. Pace depends on translator and clinician availability. Each language goes live as it is completed — value starts at ~week 8, not month 5.