Nigerian-Language Support — Proposal & Budget (Template)

Prepared for: [Insurer / Partner] Prepared by: MobiCova Health Date: [date] Status: Proposal for review — planning-grade estimates

## 1. Executive summary

This proposal sets out how MobiCova can deliver your member experience in Nigeria’s major languages — Nigerian Pidgin, Hausa, Yoruba and Igbo — across the web app, the USSD and WhatsApp channels, and the free AI Health Buddy. Together these reach the great majority of Nigerians in the language they are most comfortable using, including members on basic phones.

Our approach is safety-first and phased: we start with Nigerian Pidgin, prove the end-to-end pipeline, then add Hausa, Yoruba and Igbo in turn. Every language is professionally translated for the parts that matter most — safety, legal and consent — and signed off by a native-speaker clinician before it goes live.

Headline investment: ≈ ₦4.4M – 7.4M one-off plus ≈ ₦0.6M – 1.4M per year ongoing. The cost is driven by people (clinical and legal review), not software — because MobiCova’s platform is already built to be multilingual.

## 2. What we will deliver

Full localisation across every place a member reads or hears words from the service:

- Web application — member experience with a language switcher and a remembered preference.

- USSD — the menu-driven flows used on basic phones, fitted to each language within the on-screen character limits.

- WhatsApp — intake and the Health Buddy, with a “choose your language” step.

- Notifications — email and SMS templates.

- AI Health Buddy — answers generated in the member’s own language, grounded on clinician-reviewed sources, with the same deterministic safety net we run in English.

Languages: Nigerian Pidgin, Hausa, Yoruba, Igbo.

## 3. Languages and rollout sequence

| Order | Language | Approx. reach | Why this position |
| --- | --- | --- | --- |
| 1 | Nigerian Pidgin | ~100M+ understand it | National lingua franca; no tone marks; AI handles it strongly; cheapest. Proves the pipeline. |
| 2 | Hausa | ~80M+ | Dominant in the North; Latin script. |
| 3 | Yoruba | ~45M | South-West; tonal, needs diacritics and extra QA. |
| 4 | Igbo | ~30M | South-East; tonal, needs diacritics and extra QA. |

## 4. Our approach

Phase 0 — Foundation. Multilingual machinery (translation framework, language switcher, stored preference, string catalogue) — invisible to members, de-risks everything. Already built into the MobiCova platform.

Phase 1 — Nigerian Pidgin. First full language end-to-end: web, USSD, WhatsApp and the Buddy, including a Pidgin safety vocabulary.

Phases 2–4 — Hausa, then Yoruba, then Igbo. Each: professional translation of the interface and premium translation of safety/legal/consent wording; a language-specific safety vocabulary; native-speaker clinician review and sign-off; diacritic/rendering QA.

Safety gate. No language is switched on for the public until its safety vocabulary and clinician sign-off are complete.

## 5. Quality and safety commitments

- An in-language safety net. Detection of crisis, emergency and distress wording — routing to Nigerian helplines and 112 — is rebuilt for each language, so a cry for help is caught as reliably as in English. Verified by automated test before go-live.

- Native-speaker clinician sign-off of the Buddy’s answers and the safety vocabulary, with periodic refresh.

- Professional translation of safety, legal and consent text (not machine-only), with legal review where appropriate.

- English as a safe fallback for anything not yet translated.

## 6. Investment

Indicative planning ranges, not fixed quotes — confirm against actual translator and clinician rates. Naira primary; US-dollar approximate.

### 6.1 One-off (all four languages)

| Cost item | Driver | Indicative |
| --- | --- | --- |
| General translation (UI, USSD/WhatsApp, email/SMS) | Word count × 4 | ₦0.8M – 1.4M |
| Specialist translation (safety, legal, consent) | Premium rate × 4 | ₦0.5M – 0.9M |
| Native-speaker clinician review & sign-off | ~20–30 hrs/language | ₦2.0M – 3.0M |
| In-language safety vocabularies | Native + clinical input | ₦0.3M – 0.5M |
| Legal review of consent/disclaimers | Per language | ₦0.6M – 1.2M |
| Linguistic QA & testing | Per language | ₦0.2M – 0.4M |
| One-off total (external) |  | ≈ ₦4.4M – 7.4M (~$2.8k – 4.6k) |

### 6.2 Recurring

| Cost item | Why it recurs | Indicative |
| --- | --- | --- |
| Translation maintenance | New strings translated ×4 | ₦50k – 150k / quarter |
| Clinician re-review retainer | Content refresh | ₦100k – 200k / quarter per language |
| Localisation tooling (optional) | Translator workflow | ~$30 – 150 / month |
| AI inference uplift | Non-English answers cost more | +30 – 100% per Buddy message |

### 6.3 Costs that are easy to miss

- SMS encoding penalty. Yoruba/Igbo tone marks force Unicode SMS (~70 chars/segment) — roughly 2–3× the SMS cost. We strip tone marks on SMS to control this.

- USSD screen limits. Longer translations may need more screens, raising per-session cost; we abbreviate on USSD.

- AI cost per answer. Lower-resource languages may need a stronger model — Igbo/Hausa replies can cost 2–4× a Pidgin/English one.

- Basic-phone rendering. Some handsets won’t show tone marks; channels may use simplified spelling.

- Safety-vocabulary upkeep as slang evolves.

### 6.4 Planning envelope

≈ ₦4.4M – 7.4M one-off, then ≈ ₦0.6M – 1.4M per year (heavier while all four are active). The bulk is clinical and legal review — the safeguards that make health advice in local languages trustworthy.

## 7. How we keep the cost down

- Pidgin-first — no tone marks (no SMS/USSD penalty), strongest AI, lightest review; proves the pipeline before the indigenous three.

- The Buddy answers in-language at runtime — only fixed wording is translated; the AI handles the long tail.

- Strip tone marks on SMS/USSD only, keep full spelling on web.

- A localisation tool pays for itself once maintenance begins.

## 8. Indicative timeline

| Phase | Scope | Duration |
| --- | --- | --- |
| Phase 0 — Foundation | Already built | — |
| Phase 1 — Pidgin | First full language (web, USSD, WhatsApp, Buddy) | 4–6 weeks |
| Phase 2 — Hausa | Translation, safety vocab, sign-off, QA | 3–4 weeks |
| Phase 3 — Yoruba | As above + diacritic QA | 3–4 weeks |
| Phase 4 — Igbo | As above + diacritic QA | 3–4 weeks |

- First language live (Pidgin): ~6–8 weeks from go-ahead.

- All four complete: ~4–5 months, each going live as finished. Pace is set by translator and clinician availability.

## 9. Assumptions and exclusions

- Four languages as scoped; more multiplies translation and review lines.

- Translator and clinician availability are external lead-time dependencies.

- Voice/IVR is out of scope (text-based web, USSD, WhatsApp, SMS, email only).

- Excludes any third-party agency minimums or rush fees.

## 10. Decisions to confirm

| Decision | Options | Your choice |
| --- | --- | --- |
| Depth of localisation | UI only · + channels · + AI Buddy (recommended) | ☐ |
| Translation standard | Machine + review · professional/native for safety/legal/consent (recommended) | ☐ |
| Languages & order | All four, Pidgin → Hausa → Yoruba → Igbo (recommended) · subset | ☐ |
| Clinical assurance | Native-speaker clinician per language (recommended) | ☐ |

## 11. Next steps

- Confirm the decisions above and the budget envelope; choose the first phase to fund (we recommend Phase 1 — Pidgin).

- Identify translators and a native-speaker clinician per language.

- MobiCova produces a detailed implementation plan and delivery timeline.

- Kick off — first language live in ~6–8 weeks.

MobiCova Health — trusted digital health infrastructure for Nigeria and Africa.