Nigerian-Language Support — Proposal & Budget

Prepared for: AXA Mansard Prepared by: MobiCova Health Date: 19 June 2026 Status: Proposal for review — planning-grade estimates

## 1. Executive summary

You asked whether MobiCova plans to support Nigeria’s major languages. The answer is yes — and this document sets out exactly how we would do it, in what order, and what it costs.

We propose to localise the entire member experience — the web app, the USSD and WhatsApp channels, and the free AI Health Buddy — into four languages: Nigerian Pidgin, Hausa, Yoruba and Igbo. Together these reach the overwhelming majority of Nigerians in the language they are most comfortable using, including members on basic phones who never touch the web app.

Our approach is safety-first and phased. We start with Nigerian Pidgin (widest reach, fastest to deliver), prove the end-to-end pipeline, then add Hausa, Yoruba and Igbo in turn. Every language is professionally translated for the parts that matter most — safety, legal and consent wording — and signed off by a native-speaker clinician before it goes live.

The headline investment is ≈ ₦4.4M – 7.4M one-off plus ≈ ₦0.6M – 1.4M per year ongoing. Notably, the cost is driven by people — clinical and legal review — far more than by software.

## 2. What we will deliver

Full localisation across every place a member reads or hears words from MobiCova:

- Web application — marketing site and the member, provider, pharmacy and admin experiences, with a language switcher and a remembered language preference.

- USSD — the menu-driven flows used on basic phones (intake and the Health Buddy menu), re-fitted to each language within the strict on-screen character limits.

- WhatsApp — intake and the Health Buddy conversation, with a simple “choose your language” step.

- Notifications — email and SMS templates.

- AI Health Buddy — answers generated in the member’s own language, grounded on our trusted health sources, with the same deterministic safety net we run in English — extended to work in each new language.

Languages: Nigerian Pidgin, Hausa, Yoruba, Igbo.

## 3. Languages and rollout sequence

We deliver in this order, lowest-risk and highest-reach first:

| Order | Language | Approx. reach | Why this position |
| --- | --- | --- | --- |
| 1 | Nigerian Pidgin | ~100M+ understand it | National lingua franca; no tone marks; AI handles it strongly; cheapest. Proves the pipeline. |
| 2 | Hausa | ~80M+ | Dominant in the North; Latin script (no special encoding needed). |
| 3 | Yoruba | ~45M | South-West; tonal, needs diacritics and extra rendering QA. |
| 4 | Igbo | ~30M | South-East; tonal, needs diacritics and extra rendering QA. |

## 4. Our approach

Phase 0 — Foundation (no visible change yet). We fit the platform with the machinery to be multilingual: a translation framework, a language switcher, a stored language preference per member, and a catalogue of every English phrase in the product. English remains the fallback throughout. This de-risks everything that follows.

Phase 1 — Nigerian Pidgin. First full language end-to-end: web, USSD, WhatsApp and the AI Buddy, including a Pidgin safety vocabulary. This validates the model before we invest in the three indigenous languages.

Phases 2–4 — Hausa, then Yoruba, then Igbo. Each language: professional translation of the interface and premium, specialist translation of the safety, legal and consent wording; a language-specific safety vocabulary; native-speaker clinician review and sign-off of the Buddy’s answers; and diacritic/rendering QA for the tonal languages.

Safety gate. No language is switched on for the public until its safety vocabulary and clinician sign-off are complete — the same disciplined gate we already apply to sensitive features.

## 5. Quality and safety commitments

Health information in someone’s own language is a matter of trust and safety, not just convenience. We commit to:

- An in-language safety net. Our Buddy already detects crisis, emergency and distress wording in English and routes to the right helplines. That detection is rebuilt for each language — because a cry for help in Yoruba, Hausa, Igbo or Pidgin must be caught just as reliably as one in English. This is the single most important piece of the work.

- Native-speaker clinician sign-off. A clinician who speaks the language reviews the Buddy’s health answers and the safety vocabulary before go-live, and on a periodic refresh thereafter.

- Professional translation of safety, legal and consent text. These are not machine-translated. Where appropriate they also receive legal review, so consent and disclaimers hold up in each language.

- English as a safe fallback. If anything is ever untranslated, the member sees clear English rather than a broken screen.

## 6. Investment

All figures are indicative planning ranges, not fixed quotes — they should be confirmed against actual translator and clinician rates. Naira shown primary; US-dollar equivalents approximate.

### 6.1 One-off (to add all four languages)

| Cost item | What drives it | Indicative (all 4 languages) |
| --- | --- | --- |
| General translation (UI, USSD/WhatsApp, email/SMS) | Word count × 4 languages | ₦0.8M – 1.4M |
| Specialist translation (safety, legal, consent, disclaimers) | Premium medical/legal rate × 4 | ₦0.5M – 0.9M |
| Native-speaker clinician review & sign-off | ~20–30 hrs per language — usually the largest line | ₦2.0M – 3.0M |
| In-language safety vocabularies | Native + clinical input; safety-critical | ₦0.3M – 0.5M |
| Legal review of translated consent/disclaimers | Lawyer, per language | ₦0.6M – 1.2M |
| Linguistic QA & testing | Diacritics, USSD limits, device rendering | ₦0.2M – 0.4M |
| One-off total (external) |  | ≈ ₦4.4M – 7.4M (~$2.8k – 4.6k) |

Software build effort (the translation framework, channel re-fit and multilingual Buddy) is delivered as part of the MobiCova engagement and is shown separately in the timeline, not in the cash table above.

### 6.2 Recurring (ongoing)

| Cost item | Why it recurs | Indicative |
| --- | --- | --- |
| Translation maintenance | Every new feature/phrase must be translated into all four languages | ₦50k – 150k / quarter |
| Clinician re-review retainer | Refresh as content evolves | ₦100k – 200k / quarter per active language |
| Localisation tooling (optional) | Manages the translation catalogue and translator workflow | ~$30 – 150 / month |
| AI inference uplift | Non-English answers cost more to generate (see 6.3) | +30 – 100% per Buddy message in those languages |

### 6.3 Costs that are easy to miss

- SMS encoding penalty. Yoruba and Igbo tone marks force SMS into an encoding that fits only ~70 characters per message segment instead of 160 — roughly 2–3× the SMS cost for those two languages. We can strip tone marks on SMS only to avoid this.

- USSD screen limits. Translations run longer than English; a screen that fit in one step may need two, which can raise per-session costs and lengthen the flow. We mitigate with abbreviated wording on USSD.

- AI cost per answer. The AI uses more processing for the lower-resource languages, and the three indigenous languages may need our stronger model for safe quality — so a Buddy reply in Igbo or Hausa can cost 2–4× a Pidgin or English one. Small while usage is capped, but it scales with adoption.

- Basic-phone rendering. Some older handsets won’t display tone marks correctly, so channels may use a simplified spelling while the web app keeps full spelling.

- Safety-vocabulary upkeep. Slang evolves (Pidgin fastest), so the safety word-lists need periodic refresh to stay reliable.

### 6.4 Planning envelope

≈ ₦4.4M – 7.4M one-off, then ≈ ₦0.6M – 1.4M per year (heavier while all four languages are actively maintained). The bulk is clinical and legal review — the safeguards that make health advice in local languages trustworthy.

## 7. How we keep the cost down

- Pidgin-first is the cheap win — no tone marks (so no SMS/USSD penalty), strongest AI performance, lightest review. We prove the whole pipeline before spending on the indigenous three.

- The Buddy answers in-language at the moment of asking — so we only pay to translate the fixed wording; the AI handles the endless variety of questions.

- Strip tone marks on SMS/USSD only, keep full spelling on the web — sidesteps the encoding penalty without compromising the web experience.

- A localisation tool pays for itself once routine maintenance begins.

## 8. Indicative timeline

Engineering and the external work (translation, clinician review) run in parallel, so elapsed time is paced as much by translator and clinician availability as by build effort.

| Phase | Scope | Indicative duration |
| --- | --- | --- |
| Phase 0 — Foundation | Translation framework, language switcher, language preference, string extraction (no visible change) | 2–3 weeks |
| Phase 1 — Nigerian Pidgin | First full language end-to-end: web, USSD, WhatsApp, Buddy + Pidgin safety vocabulary | 4–6 weeks (incl. translation + clinician review) |
| Phase 2 — Hausa | Translation, safety vocabulary, clinician sign-off, QA | 3–4 weeks |
| Phase 3 — Yoruba | As above + diacritic/rendering QA | 3–4 weeks |
| Phase 4 — Igbo | As above + diacritic/rendering QA | 3–4 weeks |

- First language live (Pidgin): approximately 6–8 weeks from go-ahead (Phase 0 + Phase 1).

- All four languages complete: approximately 4–5 months elapsed, with each language going live as it is finished rather than all at the end.

## 9. Assumptions and exclusions

- Estimates assume four languages as scoped; adding more multiplies translation and review lines.

- Translation and clinician availability are external lead-time dependencies — they pace the rollout as much as engineering does.

- Voice/IVR (spoken) channels are out of scope — this covers text-based web, USSD, WhatsApp, SMS and email only.

- Figures exclude any third-party translation-agency minimums or rush fees.

## 10. What was agreed (decision log)

| Decision | Agreed position |
| --- | --- |
| Depth of localisation | Full — UI + USSD/WhatsApp + AI Buddy |
| Translation standard | Professional / native review at minimum for safety, legal and consent wording |
| Languages & order | All four, sequenced Pidgin → Hausa → Yoruba → Igbo |
| Clinical assurance | Native-speaker clinician reviews each language |

## 11. Next steps

- Confirm budget envelope and which phase to fund first (we recommend Phase 0 + Pidgin together).

- Identify translators and a native-speaker clinician per language, to firm up the people costs against real rates.

- MobiCova produces a detailed implementation plan and delivery timeline for the approved scope.

- Kick off Phase 0 (foundation) — invisible to members, but it unlocks everything that follows.

MobiCova Health — building trusted digital health infrastructure for Nigeria and Africa.