Managed Production Go-Live Plan (Path A)

Launch production on the hardened managed stack you already operate — Render + Supabase + Cloudflare — as the fastest, lowest-ops route to live. This is the bridge to AWS af-south-1 (Path C, infra/terraform/ + PRODUCTION-DEPLOYMENT-RUNBOOK.md), which your incoming DevOps engineer will execute later.

Figures are planning-grade. Target: a careful go-live in ~3–5 days.

## The plan in one line

Go live on managed now → hand the AWS af-south-1 migration to the DevOps engineer when residency / SOC 2 / scale demand it. Nothing we build here is wasted: it’s the same app, same CI promotion model, same domains.

### Residency note (interim)

The managed stack runs in the EU (Frankfurt) with a Cloudflare Lagos edge for fast African delivery. That’s NDPR-workable as an interim; true af-south-1 residency arrives with Path C. Flag this to enterprise insurer prospects as “on the roadmap”.

### Environment model (now three live tiers)

Dev (local + previews)  →  UAT (managed, today's MVP)  →  Production (managed → AWS later)
   feature/*                    push to main                    release tag vX.Y

## Target managed-production architecture

- Cloudflare — DNS, CDN, WAF, DDoS, TLS/HSTS, rate-limiting (Lagos edge).

- Render — API on render.prod.yaml: ≥2 instances + autoscale, /health, preDeploy migrate.

- Supabase (separate prod project) — HA Postgres + PITR + daily backups + (optional) read replica.

- Sentry + Better Stack — error tracking, uptime, alerting, on-call paging.

- Live integrations — Stripe/Paystack live, WhatsApp production, Resend verified domain, Anthropic prod.

## Phase 0 — Prerequisites & decisions

- Register/confirm the domain; plan app.<domain> (client) and api.<domain> (API).

- A Cloudflare account for the domain.

- Live keys ready (Stripe/Paystack live, WhatsApp prod number, Resend verified domain, Anthropic prod) — kept out of the repo.

- A separate production Supabase project (never share the UAT DB).

- Billing + spend alerts on Render and Supabase.

✓ Domain, Cloudflare, prod Supabase project, and live keys all in hand.

## Phase 1 — Production database (Supabase)

- New Supabase project, EU region, Pro/Team plan.

- Enable Point-in-Time Recovery + daily automated backups; (optional) a read replica for reporting.

- Use the IPv4 connection pooler string for DATABASE_URL — the direct host is IPv6-only and will time out.

- Run migrations against the prod DB (npm run migrate, or the release pipeline’s preDeploy).

✓ Prod DB reachable via pooler; migrations applied; PITR on; a test restore validated.

## Phase 2 — Render production services

Create the two services from render.prod.yaml (mobicova-prod-api, mobicova-prod-web): - API: Standard plan, min 2 / max 4 instances, autoscale on CPU, preDeployCommand: npm run migrate, /health check, APP_ENV=production, autoDeploy: off. - Web: static, VITE_API_URL=https://api.<domain>.

✓ Both services build green; API /health returns 200 across ≥2 instances.

## Phase 3 — Edge: Cloudflare

- DNS: app.<domain> → Render web; api.<domain> → Render API (proxied/orange-cloud).

- WAF managed ruleset + bot mitigation; rate limiting; DDoS on.

- TLS Full (strict) + HSTS; security headers; cache the static client at the edge.

✓ Site loads over HTTPS via Cloudflare; WAF blocks a test injection; headers grade A.

## Phase 4 — Secrets & live integrations

Set every sync: false var in the Render dashboard to a live value: DATABASE_URL (pooler), DATABASE_CA_CERT, JWT_SECRET (auto), CLIENT_URL/SERVER_URL, PLATFORM_ADMIN_EMAILS, ANTHROPIC_API_KEY, STRIPE_SECRET_KEY + STRIPE_WEBHOOK_SECRET, PAYSTACK_SECRET_KEY, RESEND_API_KEY + EMAIL_FROM, WHATSAPP_* (production number).

⛔ Never set OTP_DEV_MODE or DEMO_SEED_PASSWORD in production. 🔁 Turn on MFA for Render, Supabase, Cloudflare and GitHub accounts.

✓ App boots with all live secrets; no secret in logs or repo.

## Phase 5 — Observability & on-call (do this even solo)

- Sentry on client + server (release tagging).

- Better Stack uptime check on /health and a login flow, from multiple regions.

- Paging to your phone/email on downtime or error spikes.

- A simple dashboard: request rate, error rate, latency, DB health.

✓ An injected error pages you within minutes; uptime monitor is green.

## Phase 6 — CI/CD promotion

Already wired: - UAT = auto-deploy from main (uat.yml). - Production = tag vX.Y → release.yml → manual approval (GitHub production environment) → Render deploy hooks → smoke test.

Set up: the production environment with required reviewers, the two prod deploy-hook secrets (RENDER_DEPLOY_HOOK_PROD_API/_WEB), and PROD_API_URL.

✓ Tagging a release prompts for approval, deploys, and smoke-tests green.

## Phase 7 — Go-live cutover

- Final migration applied; seed only real platform admin(s) — no demo data.

- Point live webhooks at prod api.<domain>: WhatsApp (Meta), Africa’s Talking (USSD/SMS), Stripe/Paystack.

- One test payment + refund; confirm webhook receipt.

- DNS cutover (lower TTL beforehand).

- Smoke test every channel: web, WhatsApp, USSD → enrolment + membership ID, OTP login, a claim.

- Watch dashboards for the first hours; rollback ready (re-deploy the previous release).

✓ Real enrolment works on each channel; payments + OTP live; error rate flat.

## Phase 8 — Post-launch

- Verify backups; run a PITR restore test to a Supabase branch/clone.

- First-week cost + error review.

- Write a 1-page incident runbook (symptoms → who → restore steps).

## Solo-operator guardrails (until the DevOps engineer arrives)

- Lean on managed auto-everything — Supabase backups/PITR/failover, Render health-restart + autoscale. Let the platform do the ops.

- Get one paid security review before or right after go-live — highest-value single thing you can do for a health platform. (Don’t skip this.)

- Shrink the blast radius — least-privilege/scoped keys, prod secrets separate from UAT, MFA everywhere.

- Know before users do — uptime monitor + paging is non-negotiable, even for one person.

- Keep the incident runbook to one page so a 3am you (or a contractor) can follow it.

## DevOps engineer handover pack (when they start)

Point them at, in the repo: - MANAGED-GO-LIVE-PLAN.md (this) — how production runs today. - PRODUCTION-DEPLOYMENT-RUNBOOK.md + infra/terraform/ — Path C (AWS af-south-1) target. - PHASE-1-RELIABILITY-SPEC.md, ENVIRONMENTS-PLAN.md, PRODUCTION-READINESS-PLAN.md. - .github/workflows/production.yml — the AWS pipeline, currently manual; they flip its trigger to release tags at migration time and retire the managed deploy.

Their first two mandates: (1) a security review of managed production; (2) plan/execute the Path C migration to AWS af-south-1 when residency / SOC 2 / scale require it.

## Cost & timeline

- Run-rate: ~$1.2k–$2.5k/mo (managed Tier A) + variable comms (see the comms cost model).

- Setup: ~3–5 days for a careful go-live.

- Later (Path C): AWS af-south-1 build is a separate ~6–10 day DevOps effort, already specced.