Production Readiness & Cost Plan

Moving from a single-region MVP to an industrial-grade platform: fault tolerance, failover, load balancing, observability, and compliance.

All figures are planning-grade estimates in USD ranges — not quotes. They are sized to the assumptions below and will move with real traffic, comms volume, and vendor negotiation.

## 0. Assumptions locked for this plan

| Variable | Decision |
| --- | --- |
| Scale horizon | Up to ~50,000 active members |
| Data residency / region | Nigeria / Africa |
| Approach costed | Both — Tier A (hardened managed) and Tier B (cloud-native AWS), side by side |
| Compliance target | NDPR + penetration test + SOC 2 / ISO 27001 |

### The residency ↔ approach trade-off (important)

- Render (Tier A) has no African region. Tier A would run in EU (Frankfurt/London) with a Cloudflare Lagos edge for fast static/CDN delivery — data-at-rest sits in the EU.

- AWS af-south-1 (Cape Town) keeps data on-continent, and AWS has a Lagos Local Zone + CloudFront edge for low latency into Nigeria. This is the only one of the two that satisfies true African residency.

- NDPR permits cross-border transfer with adequate safeguards, so EU hosting is legally workable — but health data is sensitive and enterprise insurer buyers will ask “where does it live?”, which favours Cape Town or a local DC.

- Net: if residency + SOC 2 are firm, the destination is Tier B. Tier A is still useful as a fast interim hardening step, but avoid investing heavily in it only to migrate later.

## 1. What “industrial-grade” means here

You are buying four things:

- Availability target — e.g. 99.9% (~8.7 h/yr down), 99.95%, or 99.99%. Each extra “nine” multiplies cost.

- Fault tolerance / failover — no single server, Availability Zone, or DB instance can take the platform down.

- Recoverability — RPO (max data loss, target ≤ 5 min) and RTO (max downtime to recover, target ≤ 30 min) via standby + point-in-time backups.

- Security & compliance — health data + payments + Nigerian PII → NDPR, PCI offloaded to Stripe/Paystack, and SOC 2 / ISO 27001 for enterprise procurement.

Recommended target for 50k: 99.9% availability, RPO ≤ 5 min, RTO ≤ 30 min.

## 2. Target architecture (vs. today)

| Layer | MVP today | Industrial-grade target |
| --- | --- | --- |
| DNS / edge | Render domain | Cloudflare DNS + CDN + WAF + DDoS, Lagos edge |
| Frontend | Render static | Static on CDN (already cheap & resilient) |
| API | 1 Render service | ≥2 containers, multi-AZ, behind a load balancer, auto-scaling, health-checked & auto-replaced |
| Database | Supabase (single) | Managed HA Postgres — primary + standby (auto-failover), read replica, PITR backups |
| Cache / queue | none | Redis (sessions, rate-limit, cache) + job queue (emails, webhooks, OTP) so spikes don’t block requests |
| Object storage | Supabase Storage | S3 / multi-AZ object storage (fine as-is) |
| Secrets | env vars | Managed secrets store + rotation |
| Observability | console logs | Logs + metrics + traces + error tracking + uptime alerts + on-call |
| Delivery | manual git push | CI/CD with staging + blue-green/canary deploys, infra-as-code (Terraform) |
| Region | one | Africa-proximate + optional multi-region DR (later) |

## 3. Tier A vs Tier B — side by side

| Dimension | Tier A — Hardened Managed | Tier B — Cloud-native AWS |
| --- | --- | --- |
| Stack | Render (scaled) + Supabase Team + Cloudflare + Upstash + Sentry/Better Stack | ECS Fargate + RDS/Aurora Multi-AZ + ElastiCache + CloudFront + WAF + Datadog/Grafana, on Terraform |
| Region | EU (Frankfurt/London) + Lagos CDN edge | AWS af-south-1 (Cape Town) + Lagos edge — true African residency |
| Scales to | Tens of thousands comfortably | Millions |
| Ops burden | Low (vendor-managed) | Higher (you own the infra) |
| SOC 2 / ISO fit | Workable (rely on sub-processor reports) | Stronger control & evidence story |
| Setup effort | ~2–4 weeks | ~6–10 weeks |
| Best as | Fast interim hardening | The destination for your requirements |

## 4. Monthly run-rate (infrastructure only) at ~50k members

### Tier A — Hardened Managed (EU-hosted)

| Item | Est. /month |
| --- | --- |
| Render API — 2–3 instances, autoscale + HA | $200 – $500 |
| Supabase Team + compute upgrade + read replica + PITR | $700 – $1,400 |
| Cloudflare Pro/Business (WAF, DDoS) | $20 – $250 |
| Upstash Redis | $10 – $100 |
| Resend (email) | $20 – $90 |
| Monitoring (Sentry + Better Stack) | $50 – $300 |
| Subtotal | ≈ $1,200 – $2,500 / mo |

### Tier B — Cloud-native AWS (af-south-1, ~20–30% region premium included)

| Item | Est. /month |
| --- | --- |
| ECS Fargate (2–3 tasks, multi-AZ) + ALB | $130 – $350 |
| RDS/Aurora PostgreSQL Multi-AZ (+ read replica) | $300 – $700 |
| ElastiCache Redis (multi-AZ) | $60 – $150 |
| S3 + CloudFront (Lagos edge) | $30 – $150 |
| WAF + Shield Standard | $30 – $100 |
| NAT gateway, Secrets Manager, data transfer | $100 – $250 |
| Observability (Datadog, or cheaper self-hosted Grafana) | $200 – $600 |
| Subtotal | ≈ $1,500 – $3,000 / mo |

At 50k scale the two run-rates are close (~$1.2k–$3k/mo). The real difference is setup cost, ops burden, residency, and headroom — not the monthly server bill.

## 5. The costs that dominate at scale (usage-based — often bigger than servers)

| Variable cost | Driver | Order of magnitude at ~50k |
| --- | --- | --- |
| WhatsApp Business | per-template-message (Meta), Nigeria | ~$0.01–$0.05 each → $1k–$10k/mo, volume-driven |
| SMS / OTP | per-message via Termii/Africa’s Talking/telco | local routes cheap (~$0.002–0.003); intl OTP pricier |
| USSD sessions | telco / Africa’s Talking per-session + shortcode rental | volume-driven; possible revenue-share |
| Claude (AI triage) | per-token usage | ~$200–$1,500/mo at moderate use |
| Payments | Paystack ~1.5% / Stripe ~2.9% | % of money moved (pass-through) |

Lever: prefer cheaper utility/auth WhatsApp templates over marketing ones, batch notifications, and route OTP through local Nigerian SMS aggregators to control this line.

## 6. One-time setup costs

| Workstream | Tier A | Tier B |
| --- | --- | --- |
| Infra build-out / IaC / CI/CD / staging / monitoring / runbooks | $8k – $25k (~2–4 wks) | $30k – $70k (~6–10 wks) |
| Data migration (Supabase → target) | minimal | included above |
| Load & failover testing | included | included |

(Lower end assumes we build it together; upper end assumes a contract DevOps engineer.)

## 7. SOC 2 / ISO 27001 + security (year one)

| Item | Year-one cost |
| --- | --- |
| Compliance automation platform (Vanta / Drata / Secureframe) | $7k – $25k |
| SOC 2 Type II auditor (Type I first, then Type II) | $12k – $30k |
| ISO 27001 certification body audit | $10k – $25k |
| Penetration test | $5k – $20k |
| vCISO / consultant (optional, if no in-house security lead) | $2k – $6k /mo |
| Year-one total (excl. vCISO) | ≈ $40k – $90k |
| Recurring thereafter | ≈ $20k – $40k / yr |

⏱ Timeline note: SOC 2 Type II requires an observation window (typically 3–12 months). Start the controls + tooling early; certification follows the window. ISO 27001 similarly runs a Stage 1 + Stage 2 audit over a few months.

## 8. Ongoing people / ops

|  | Tier A | Tier B |
| --- | --- | --- |
| DevOps / SRE coverage | light — fractional, a few hrs/mo ($0–$2k/mo) | real coverage — fractional $2k–$6k/mo or a hire |
| On-call | optional | recommended |

People are frequently the single largest real line item once you’re live.

## 9. Recommended path & first-year budget

Given Africa residency + SOC 2/ISO are firm, the destination is Tier B (AWS af-south-1). To avoid building twice, go cloud-native but keep it right-sized for 50k, and layer compliance over a window rather than all at once.

Phase 1 — Reliability foundation (now, ~2–4 wks): HA database + PITR, ≥2 API instances + load balancer, Cloudflare WAF, CI/CD + staging, monitoring + alerting, a job queue. Biggest reliability gain per dollar. Can start on the managed stack for speed.

Phase 2 — Cloud-native cutover (when procurement/scale demands, ~6–10 wks): Terraform on AWS af-south-1, ECS + RDS Multi-AZ + ElastiCache, migrate data, load-test, runbooks.

Phase 3 — Compliance window (start in parallel with Phase 2): Vanta/Drata, pen test, SOC 2 Type I → Type II, ISO 27001. Budget the 3–12 month observation window.

Phase 4 — Multi-region DR (only if a 99.99% SLA is contractually required).

### Indicative year-one all-in (recommended Tier B path)

| Bucket | Year-one |
| --- | --- |
| Infra build-out / setup | $30k – $70k |
| Infra run-rate (~$2k–$3k/mo × 12) | $24k – $36k |
| SOC 2 + ISO + pen test | $40k – $90k |
| DevOps / SRE (~$2k–$6k/mo × 12) | $24k – $72k |
| Subtotal (excl. variable comms & payments) | ≈ $118k – $268k |
| Variable comms (WhatsApp/SMS/USSD) + AI | usage-driven; $18k–$130k+/yr at volume |

The headline: at 50k members, servers are the small part. Setup, compliance, people, and per-message comms are what move the budget — plan around those.

## 10. Decision summary

- Run reliability now on a hardened stack (Phase 1) — quick win, low cost.

- Land on AWS af-south-1 (Tier B) for residency + SOC 2 fit — don’t over-invest in EU managed.

- Start the compliance window early — it’s gated by time, not money.

- Engineer comms costs (WhatsApp template type, local SMS routing) — the real scale lever.

- Defer multi-region until a contract demands 99.99%.

Architecture diagrams

Target production architecture (Tier B, AWS af-south-1)

Fault tolerance & failover (multi-AZ)

Data residency & network boundary (SOC 2)

Phased roadmap